Project plan

5.mar – Planning meeting
6.mar. – Possible morning in lab, synthesis
7.mar – 12.3 Prepare presentation + 3x coursework
12.mar – Presentation Management of Innovation and Technology
14.mar - Prepare samples using RT (9-13)
15.mar – Deadline ethical coursework
18-22 mar – Work in lab (sample prep: different loadings using hydrothermal approach)
22.mar – Deadline MEMS-design coursework
25.mar – Deadline MOTI report
25. mar-18. April – Project work + preparing for exam
11-14. Apr – Anders possibly away.
24. Apr - 1st exam
29. Apr - 2nd exam
30. Apr onwards – Project work

?? - SEM training
?? - XRD training (Demonstrator to perform)
?? - AFM/nanoindent (Demonstrator (wei) to preform)

Samples to be prepared:
Cellulose sponges loaded with ZIF: 1.	With RT synthesis (like before X-mas)
2.	Loading with hydrothermal method[1]
[1] http://pubs.rsc.org/en/content/articlelanding/2010/JM/C0JM00515K
3.	Different types of cellulose (Aminolated (NH2-terminated + carboxylated(?))
4.	Different sizes of cellulose sponges.
5.	Test for chemical and thermal stability(?)
Cellulose nano-fibres:	1.	Varying the concentrations of ZIF/fibres
2.	Prepare samples for gas permeation measurements (size(?) and uniformity issues?)

Characterization:	1.	SEM:
2.	Nanoindentation: Ask Wei for help
3.	Stress-strain:
4.	XRD: Emma and ask Mary Vickers or Andrew Moss for guidance regarding preparation of the samples (height etc). Both cellulose without any loading + with ZIF-loading.
5.	TGA
6.	Gas Permeation: Issan?
7.	Shear: resonant ultrasound, Michael Carpenter Earth science
8.	Gas sorption measurements: before and after stress testing and of cellulose fibre samples.